## Gantt chart
Level | WBS | Task Name | Start | Finish | % Complete | Duration | Predecessors | Milestone | Owner | Notes | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19
1 | 1 | Plan and design | 2027-01-04 | 2027-02-05 | 40% | 25 |  | No |  | A phase: its tasks have Level 2.
2 | 1.1 | Kickoff and scope | 2027-01-04 | 2027-01-08 | 100% | 5 |  | No | Ana | Done, so the bar is dark.
2 | 1.2 | Sitemap and wireframes | 2027-01-11 | 2027-01-22 | 50% | 10 | 1.1 | No | Ben | Half done: one week dark.
2 | 1.3 | Visual design | 2027-01-25 | 2027-02-05 | 0% | 10 | 1.2 | No | Ben
2 | 1.4 | Design signed off | 2027-02-05 | 2027-02-05 | 0% | 0 | 1.3 | Yes | Ana | A milestone: Milestone is Yes.
1 | 2 | Build and launch | 2027-02-08 | 2027-03-12 | 0% | 25 |  | No
2 | 2.1 | Build pages | 2027-02-08 | 2027-02-26 | 0% | 15 | 1.4 | No | Chen
2 | 2.2 | Write and load content | 2027-02-15 | 2027-02-26 | 0% | 10 | 1.4FS+5d | No | Dana | Five working days after 1.4.
2 | 2.3 | Test and fix | 2027-03-01 | 2027-03-10 | 0% | 8 | 2.1, 2.2 | No | Chen | Waits for 2.1 and 2.2.
2 | 2.4 | Go live | 2027-03-11 | 2027-03-12 | 0% | 2 | 2.3 | No | Ana

## How to use
Excel Gantt chart template, from Onplana (onplana.com/templates/excel-gantt-chart)
How the bars work
The coloured cells right of Notes are the Gantt chart. They are conditional formatting, not a picture and not a macro:
- light blue: the weeks between a task's Start and Finish
- dark blue: the share of the task that is done, from % Complete
- dark grey: a phase (Level 1), across its whole span
- amber: a milestone (Milestone is Yes), in the week of its Finish
Make it your plan
1. Type over the example rows: a name, a Start and a Finish date, and the % Complete. The bars redraw as you type.
2. Level 1 is a phase, Level 2 a task under it. WBS numbers the rows (1, 1.1, 1.2), and Predecessors names the rows a task waits for, such as 1.2 or 1.4FS+5d.
3. Duration counts the working days from Start to Finish for you.
4. To move the chart, type a new Monday in the first date right of Notes. The other weeks follow it.
5. To add rows, type under the last one. The bars are set up to row 200.
6. For more weeks, select the last week column, copy it, and paste it to the right. Excel copies the formatting rules with it.
When the plan outgrows the sheet
Moving one date in Excel moves nothing else, so dependent tasks have to be shifted by hand. Drop this file on onplana.com/templates/excel-gantt-chart
to see it as a Gantt chart with its links, or open it in Onplana Schedule, the free desktop app for Windows and Mac, which reschedules it for you.
Keep the column names in row 1 as they are, so the file opens there unchanged.